## SOC2 Controls
Control ID | Trust Principle | Control Objective | Control Description | Owner | Frequency | System | Evidence Source | Type I Ready | Type II Evidence Available | Gap | Remediation | Status | Previous Status (2026-10-15)
CC1-01 | Security (CC1 Control environment) | Management sets the tone for security | Approved information security policy and code of conduct, reviewed yearly | Management | Annual | Organisation | NOT EVIDENCED; docs/security/policies/01_Information_Security_Policy.md (DRAFT - MANAGEMENT APPROVAL REQUIRED; not evidence) | NO | NO | Policy set exists only as DRAFT (15 documents, 0 approved, 0 operating) | Approve the drafts (SD-16, EXT-17) | NOT READY | NOT READY
CC1-02 | Security (CC1 Control environment) | Security responsibilities are assigned | Named ISMS lead, CKAM system owner, backup owner, restore owner, deploy operator, incident coordinator | Management | Annual | Organisation | docs/ai/CKAM_PRODUCTION_SERVER_CHECKLIST.md (owners not yet assigned); docs/security/policies/01_Information_Security_Policy.md roles (DRAFT) | NO | NO | Roles drafted, nobody appointed | Approve RACI (EXT-17, EXT-36) | NOT READY | NOT READY
CC1-03 | Security (CC1 Control environment) | Personnel with privileged access are trustworthy | Background screening and confidentiality agreements for privileged staff | HR | At hire | Organisation | NOT EVIDENCED | NO | NO | Not evidenced | EXT-32 | NOT READY | NOT READY
CC1-04 | Security (CC1 Control environment) | Staff know their security duties | Annual security awareness training incl. CKAM admins | HR; ISMS lead | Annual | Organisation | NOT EVIDENCED; docs/security/policies/10_Security_Awareness_Plan.md (DRAFT) | NO | NO | Not evidenced | EXT-32 | NOT READY | NOT READY
CC2-01 | Security (CC2 Communication) | The system and its boundaries are described | System description: components, data flows, trust boundaries, data stores | ISMS lead; Dev lead | Annual / on major change | CKAM | docs/ai/PRODUCTION_INFRASTRUCTURE.md; docs/security/CKAM_THREAT_MODEL.md; docs/ai/ERP_INTEGRATION.md | PARTIAL | N/A (document) | No formal SOC 2 system description | Write system description from the threat model | PARTIAL | PARTIAL
CC2-02 | Security (CC2 Communication) | Users can report problems and security events | Report a problem in the app; reference id on every error; security-event reporting channel | ISMS lead | Continuous | CKAM | backend/app/observability/client_reports.py; frontend/src/features/support/report-problem-store.ts; client_report table | YES (tooling) | SOURCE EXISTS - no observation period | Security-event reporting not communicated to staff | EXT-20, EXT-32 | PARTIAL | PARTIAL
CC2-03 | Security (CC2 Communication) | External parties are informed of commitments | Privacy notice to staff; security contact; commitments to suppliers | Legal; Management | Annual | Organisation | NOT EVIDENCED | NO | NO | Not evidenced | EXT-31 | NOT READY | NOT READY
CC3-01 | Security (CC3 Risk assessment) | Risks are identified and assessed | CKAM risk register reviewed and approved yearly and after major change | ISMS lead; Management | Annual | CKAM | docs/security/CKAM_ISO27001_READINESS.md (draft register, 31 risks); docs/security/CKAM_ISO27001_READINESS.md section 9 (draft register re-scored 2026-10-16: 40 risks); docs/security/policies/12_Risk_Management_Procedure.md (DRAFT) | PARTIAL | NO | Register is a draft; not owned or approved | Approve and own the register (EXT-36) | PARTIAL | PARTIAL
CC3-02 | Security (CC3 Risk assessment) | Fraud risk is considered | Asset misappropriation risk: custody ledger, movement audit, physical verification | Management | Annual | CKAM | docs/security/CKAM_ISO27001_READINESS.md R-09; asset_event ledger | PARTIAL | SOURCE EXISTS - no observation period | No periodic physical verification evidenced | Annual physical verification against CKAM register | PARTIAL | PARTIAL
CC3-03 | Security (CC3 Risk assessment) | Changes are assessed for security impact | Every new route needs an authorization test incl. cross-company and cross-work-area; file routes need a file-security review | Dev lead | Per change | CKAM | docs/security/CKAM_SECURITY_BASELINE.md; backend/tests/observability/test_coverage_walker.py; docs/security/CKAM_SECURITY_BASELINE.md (closure rules added 2026-10-16) | PARTIAL | NO | Baseline new, not yet approved | Approve baseline; include checklist in change record | PARTIAL | PARTIAL
CC4-01 | Security (CC4 Monitoring) | Controls are tested periodically | Internal audit of CKAM controls by someone independent of development | Management | Annual | Organisation | NOT EVIDENCED; docs/security/policies/13_Internal_Audit_Checklist.md (DRAFT, never used) | NO | NO | No internal audit | EXT-36 | NOT READY | NOT READY
CC4-02 | Security (CC4 Monitoring) | Deficiencies are tracked to closure | Findings register with severity, owner, status and retest | Dev lead; ISMS lead | Continuous | CKAM | docs/ai/REVIEW_FINDINGS.md; docs/security/evidence/access/findings.csv; docs/security/CKAM_EXTERNAL_SECURITY_ACTIONS.md; docs/security/CKAM_SECURITY_CLOSURE_REGISTER.md; docs/security/CKAM_SECURITY_FINDINGS_REGISTER.md | PARTIAL | PARTIAL (git history) | Trackers exist as documents; no owned tracker with due dates operating | Single tracker with due dates | PARTIAL | PARTIAL
CC5-01 | Security (CC5 Control activities) | Policies are turned into procedures | Security baseline and guardrails are mandatory for every change | Dev lead | Per change | CKAM | docs/ai/DEVELOPMENT_GUARDRAILS.md; docs/security/CKAM_SECURITY_BASELINE.md; Baseline updated 2026-10-16 (still not approved) | PARTIAL | NO | Baseline not approved | Approve baseline | PARTIAL | PARTIAL
CC5-02 | Security (CC5 Control activities) | Technology general controls are selected | IT general controls for servers (patching, AV, backups, access) | IT/Infra | Annual | 10.0.1.98, 10.0.0.205, NAS | NOT EVIDENCED | NO | NO | Server ITGCs not evidenced | EXT-09, EXT-37, EXT-08 | NOT READY | NOT READY
CC6-01 | Security (CC6 Logical access) | Only authorised roles can perform each action | Backend-authoritative role checks on every route (capabilities.py, deps.py) | Dev lead | Continuous; retest per release | CKAM API | docs/security/evidence/access/authz_matrix.csv (217 routes x 11 personas); docs/security/evidence/access/tests.csv (0 privilege escalation); docs/security/evidence/closure/retest2/access/authz_matrix.csv (final code: 217 routes x 14 identities = 3,038 cells, 0 escalations) | YES | SOURCE EXISTS - PERMISSION_DENIED rows in audit_log; no observation period | None for role enforcement | Re-run matrix each release | READY | READY
CC6-02 | Security (CC6 Logical access) | Users see only their company, work area or own assets | Company, work-area and own-custody scoping on every read and write | Dev lead | Continuous | CKAM API | docs/security/evidence/access/tests.csv (208 IDOR/BOLA cases); backend/tests/core/test_security_read_scope.py; AC-1, AC-2, IF-03 FIXED and retested (commits 77431ba, 7e57844); docs/security/evidence/closure/retest2/access/tests.csv (319 cases, 318 PASS, 1 OBS) | YES (code) / NO (production) | SOURCE EXISTS - no observation period | Only deployment is missing: production 3b5e842 lacks the AC-1, AC-2 and IF-03 fixes | Deploy (EXT-01) | READY IN CODE - NOT DEPLOYED | PARTIAL
CC6-03 | Security (CC6 Logical access) | User accounts are provisioned with approval | New login: account created, temporary password shown once, must change at first sign-in | CKAM owner | Per request | CKAM | audit_log CREATE rows; SECURITY PASSWORD_RESET rows; docs/security/evidence/auth/tests.csv AU-T050; docs/security/policies/03_Joiner_Mover_Leaver_Procedure.md and templates/joiner_mover_leaver_record.md (DRAFT) | PARTIAL | SOURCE EXISTS - no request/approval record | No request or approval record outside CKAM | Access request form or ticket (EXT-33) | PARTIAL | PARTIAL
CC6-04 | Security (CC6 Logical access) | Leavers lose access promptly | Deactivate or switch off login on the leaving day | HR; CKAM owner | Per leaver | CKAM | backend/tests/auth/test_vapt_sessions.py (AU-07 FIXED: token_version ends sessions on deactivation, login switch-off, role/area/company/password change); backend/tests/auth/test_wpa2_token_version_atomic.py (atomic session version; server-side refresh sessions ended too); docs/security/policies/03 (DRAFT) | PARTIAL | SOURCE EXISTS - audit UPDATE rows on asset_user | No HR trigger; fix not deployed | EXT-33; EXT-01 | PARTIAL | PARTIAL
CC6-05 | Security (CC6 Logical access) | Access is reviewed periodically | Quarterly review of all CKAM logins, roles, companies, work areas and head-office admins | CKAM owner | Quarterly | CKAM | GET /api/asset-users/export (exists); review sign-off NOT EVIDENCED; docs/security/policies/11_Periodic_Access_Review_Procedure.md and templates/access_review_record.md (DRAFT, never run) | NO | NO | No review performed | EXT-18 | NOT READY | NOT READY
CC6-06 | Security (CC6 Logical access) | Privileged access is restricted and recorded | Head-office admin grant/revoke audited; Full Admin cannot reset head-office admin; D6 open | CKAM owner | Continuous | CKAM | audit_log SECURITY PRIMARY_OWNER_GRANTED/_REVOKED, ACCESS_CHANGED; docs/ai/DECISIONS.md 2026-10-14 (1) | PARTIAL | SOURCE EXISTS - no observation period | Full Admin not company-scoped (D6); no MFA | EXT-26, EXT-19 | PARTIAL | PARTIAL
CC6-07 | Security (CC6 Logical access) | Passwords are strong and stored safely | Argon2id hashing; password policy (length, common words incl. with numbers); no plaintext anywhere | Dev lead | Continuous | CKAM | docs/security/evidence/auth/tests.csv AU-T044..AU-T049; backend/app/auth/password_policy.py; backend/tests/auth/test_vapt_password_policy.py (AU-08 FIXED); stricter name look-alike password check and a refusal text naming both secret rules (7b039fb); docs/security/policies/02_Access_Control_Policy.md (DRAFT) | YES (code) / NO (production) | N/A (configuration) | No written password policy; fix not deployed | Policy (EXT-17); deploy (EXT-01) | PARTIAL | PARTIAL
CC6-08 | Security (CC6 Logical access) | Privileged users use multi-factor authentication | MFA for head-office admin and Full Admin | Management; Dev lead | Continuous | CKAM | Not present | NO | NO | MFA absent | EXT-19 | NOT READY | NOT READY
CC6-09 | Security (CC6 Logical access) | Password guessing is blocked | Lockout after 5 failures for 15 minutes; per-address rate limit (20 sign-ins per minute, 429); constant-time sign-in; race-safe lockout counter | Dev lead | Continuous | CKAM | backend/app/core/rate_limit.py; backend/tests/auth/test_rate_limit.py, test_vapt_login.py (AU-01, AU-03, AU-16 FIXED; AU-04 MITIGATED; AU-02 ACCEPTED); audit_log LOGIN_FAILED / LOCKED rows; docs/security/evidence/closure/retest2/sessions/raw/a3_ratelimit.json and a7_timing.json (rate limits via nginx and direct, timing medians within 3.8 ms); docs/security/evidence/closure/backend/AU-04_OPTIONS.md | YES (code) / NO (production) | SOURCE EXISTS - no observation period | Not deployed; AU-04 lock-out DoS needs an owner decision (options A/B/C, recommendation C); per-address limit shared behind office NAT needs a per-office policy (EXT-40, EXT-49) | Deploy (EXT-01); monitor 429s (EXT-22) | READY IN CODE - NOT DEPLOYED | PARTIAL
CC6-10 | Security (CC6 Logical access) | Sessions end when they should | 15-minute access token; 8-hour refresh; refresh token rotated once with server-side reuse detection (auth_session stores only a SHA-256 of the token id; reuse => 401, every session of that person ended, REFRESH_REUSE row; 10 s grace for parallel tabs, REFRESH_DUPLICATE row); logout signs out everywhere; token_version raised atomically | Dev lead | Continuous | CKAM | backend/tests/auth/test_vapt_sessions.py; migration f9a1c3e5b7d2 (token_version); AU-05, AU-07 FIXED; AU-06 MITIGATED (rotation per refresh; an old rotated token stays valid until sign-out or expiry); backend/tests/auth/test_wpa2_refresh_reuse.py; backend/tests/auth/test_wpa2_token_version_atomic.py; migration b5d7f9a1c3e5 (auth_session); docs/security/evidence/closure/retest2/sessions/raw/a1_refresh.json, a2_revocation.json (AU-06 FIXED in code) | YES (code) / NO (production) | N/A (configuration) | Not deployed; residual 10 s grace window (R-34); no absolute session lifetime (decision, EXT-50) | Deploy (EXT-01) | READY IN CODE - NOT DEPLOYED | PARTIAL
CC6-11 | Security (CC6 Logical access) | Data in transit is encrypted | HTTPS for all browser traffic; Secure cookie; HSTS | IT/Infra | Continuous | 10.0.1.98 | docs/ai/PRODUCTION_INFRASTRUCTURE.md (plain HTTP, IF-02) | NO | NO | Plain HTTP over the internet | EXT-04 | NOT READY | NOT READY
CC6-12 | Security (CC6 Logical access) | Data at rest is protected | Disk/database encryption on 10.0.0.205 and NAS; encrypted backups | IT/Infra | Continuous | 10.0.0.205, NAS | NOT EVIDENCED; backups unencrypted (IF-08) | NO | NO | Not evidenced / missing | EXT-08 | NOT READY | NOT READY
CC6-13 | Security (CC6 Logical access) | Secrets are protected and rotated | JWT secret, DB, NAS and ERP passwords kept in admin-only files, rotated after exposure and on schedule; password manager | IT/Infra | On exposure; annual | 10.0.1.98 | docs/ai/PRODUCTION_INFRASTRUCTURE.md (shared\.env and nas.pw Administrators/SYSTEM only); IF-01 exposure; docs/security/CKAM_URGENT_PRODUCTION_SECURITY_RUNBOOK.md phases 8-11 (rotation prepared, NOT executed) | NO | NO | Rotation after IF-01 pending; no vault | EXT-02, EXT-23 | NOT READY | NOT READY
CC6-14 | Security (CC6 Logical access) | Network access is limited | Firewall rule for 3211; pg_hba limits app role to 10.0.1.98/32; internet port-forward | IT/Infra | Quarterly review | Network | docs/ai/PRODUCTION_INFRASTRUCTURE.md; docs/security/CKAM_HTTPS_IMPLEMENTATION_PLAN.md (prepared) | PARTIAL | NO | Internet port-forward of 3211; shared hosts | EXT-05, EXT-24 | PARTIAL | PARTIAL
CC6-15 | Security (CC6 Physical access) | Physical access to servers is restricted | Server room access control | Facilities | Continuous | Server room | NOT EVIDENCED | NO | NO | Not evidenced | Confirm and evidence | NOT READY | NOT READY
CC6-16 | Security (CC6 Logical access) | Files are handled safely | Upload allowlist, size caps, server-generated paths, attachment download, scoped access; static route containment | Dev lead | Continuous | CKAM | docs/security/evidence/input/raw_sql_review.md section 8; backend/tests/test_static_frontend.py; backend/tests/documents/test_vapt_content_check.py; IF-01, IN-02, IN-03 FIXED and retested; backend/tests/test_static_frontend_windows.py (lexical Windows-path refusal before any filesystem call); backend/tests/test_static_frontend_spa_assets.py; docs/security/evidence/closure/windows/ (native Windows: fixed code refused 28 of 28 payloads, 0 leaks) | YES (code) / NO (production) | N/A (configuration) | Not deployed: production 3b5e842 still serves files outside the frontend folder (IF-01) until EXT-01; secret rotation is CC6-13 | EXT-01, EXT-02 | READY IN CODE - NOT DEPLOYED | PARTIAL
CC6-18 | Security (CC6 Logical access) | The web application resists common browser and request attacks | Content-Security-Policy (self-hosted fonts, no Google hosts) and Permissions-Policy; security headers exactly once; no source maps; API docs off with JSON 404 for docs paths and unknown /api; request-size limits (64 KB sign-in, 5 MB JSON, 16 MB uploads, 413); unset or unknown ENVIRONMENT_NAME treated as production; no server banner; uvicorn without proxy-header trust | Dev lead | Continuous | CKAM | backend/tests/test_vapt_headers_and_docs.py; backend/tests/core/test_body_limit.py; backend/tests/core/test_production_secret_guard.py; frontend/vite.config.ts; frontend/e2e/security.spec.ts (AU-11, AU-12, AU-14, AU-15, IF-14, N1, N4 FIXED); frontend/scripts/check-build-security.mjs (npm run check:build: 0 .map files, no Google host); frontend/scripts/check-nginx-live.mjs; frontend/src/security/nginx-config.test.ts; backend/tests/core/test_n2_forwarded_for.py; docs/security/evidence/closure/wpf/WPF_RESULTS.md | YES (code) / NO (production) | N/A (configuration) | Not deployed; the production launcher must start uvicorn with --no-proxy-headers --no-server-header (EXT-38) | EXT-01; EXT-38 | READY IN CODE - NOT DEPLOYED | PARTIAL
CC6-19 | Security (CC6 Logical access) | The application database account has least privilege | Owner / migrator / runtime role split: the runtime role owns nothing, cannot TRUNCATE, ALTER, DROP or disable triggers, has INSERT/SELECT only on append-only tables and USAGE/SELECT only on sequences; role settings RESET ALL; ops/db/check_least_privilege.sql re-run after every deploy | DBA; Dev lead | Per deploy (check); continuous (grants) | PostgreSQL 10.0.0.205 | ops/db/role_split.sql, role_split_verify.sql, check_least_privilege.sql, ROLE_SPLIT_RUNBOOK.md; docs/security/evidence/closure/db/WPB_RESULTS.md (disposable DB: runtime role 7/7 needed actions, 40/40 forbidden refused; verify 45/45; 34 least-privilege checks); docs/security/evidence/closure/retest2/infra/raw/db6b_03_runtime_attacks.out.txt; backend/tests/security/test_least_privilege_role_split.py | YES (scripts, disposable DB) / NO (production) | NO (never run in production; the per-deploy check output would become the evidence) | Production runtime role ckassetapp still owns the tables; the DBA must run the updated scripts (sequence-privilege fix, RESET ALL) | EXT-07, EXT-45, EXT-46 | READY IN CODE - NOT DEPLOYED | NEW 2026-10-16
CC6-17 | Security (CC6 Physical access) | Equipment is disposed of securely | Wipe before disposal; CKAM Disposed/Scrapped status with certificate | IT | Per disposal | CKAM; organisation | CKAM disposal statuses exist; wiping NOT EVIDENCED | NO | NO | Wiping not evidenced | Procedure + certificate upload | NOT READY | NOT READY
CC7-01 | Security (CC7 System operations) | Security events are logged | Sign-in, failed sign-in, lockout, logout, password change/reset, access change, permission denied, suspicious input | Dev lead | Continuous | CKAM | docs/ai/LOGGING_AND_DIAGNOSTICS.md section 2; docs/security/evidence/auth/tests.csv AU-T096; Closure (not deployed): SECURITY rows REFRESH_REUSE, REFRESH_DUPLICATE and RATE_LIMITED added next to LOGIN_FAILED, LOCKED, INVALID_TOKEN, PERMISSION_DENIED | YES | SOURCE EXISTS - audit_log kept forever; no observation period | None | Keep | READY | READY
CC7-02 | Security (CC7 System operations) | Audit records cannot be altered | Append-only UPDATE/DELETE/TRUNCATE guards on audit_log, asset_event, asset_field_change, master_audit; audit purge refused for rows younger than 5 years; owner/runtime role split | DBA; Dev lead | Continuous | PostgreSQL | docs/security/evidence/infra/db_03_append_only_privilege_tests.out.txt; db_04_least_priv_flag_bypass.out.txt; migration a3c5e7f9b1d4; backend/tests/observability/test_vapt_append_only.py (IF-05/IF-06/AU-10 MITIGATED); migration c6e8a0b2d4f6 (DB guard on asset.status / holder / status_since); ops/db/role_split.sql and check_least_privilege.sql; docs/security/evidence/closure/db/WPB_RESULTS.md | PARTIAL | N/A (configuration) | Production owner role can still drop triggers until the role split (EXT-07, EXT-45); the lifecycle guard is marker-based (R-36); nothing deployed | EXT-07 role split; EXT-01 | PARTIAL | PARTIAL
CC7-03 | Security (CC7 System operations) | Audit logs are reviewed | Weekly review of SECURITY rows (failed logins, lockouts, access changes, permission denied) | CKAM owner | Weekly | CKAM | GET /api/admin/logs/audit (exists); review record NOT EVIDENCED; LOGS_VIEWED rows record that a review screen was opened; docs/security/policies/05_Incident_Response_Plan.md (DRAFT) names the weekly review; not operating | NO | NO | No review performed or recorded | EXT-22 | NOT READY | NOT READY
CC7-04 | Security (CC7 System operations) | Problems are detected quickly | Alerts for 5xx spikes, lockouts, backup failure, ERP sync failure, service down | IT/Infra | Continuous | CKAM; servers | NOT EVIDENCED (data exists in error_log, system_event) | NO | NO | No alerting: audit-write failure lines (log_write_failed), REFRESH_REUSE and RATE_LIMITED rows are not alerted on (EXT-22, EXT-48) | EXT-22 | NOT READY | NOT READY
CC7-05 | Security (CC7 System operations) | Vulnerabilities are found and fixed | Monthly dependency audit (npm audit, pip-audit); fix SLAs by severity | Dev lead | Monthly | CKAM | docs/security/evidence/infra/dependency_audit.md (one-off 2026-10-15); docs/security/evidence/closure/backend/dependency_recheck.md; docs/security/evidence/closure/infra/npm_audit_recheck.md; docs/security/policies/06_Vulnerability_Management_Procedure.md (DRAFT) | PARTIAL | NO | Not scheduled; no SLA | EXT-09, EXT-12 | PARTIAL | PARTIAL
CC7-06 | Security (CC7 System operations) | Independent penetration testing | External VAPT by an independent firm | Management | Annual | CKAM | Internal VAPT only (docs/security/evidence/); Internal VAPT plus two internal closure retests (docs/security/evidence/closure/retest1, retest2); no independent firm | NO | NO | No independent test | EXT-14 | NOT READY | NOT READY
CC7-07 | Security (CC7 System operations) | Systems are patched | OS, Python runtime, PostgreSQL and NAS firmware patched to policy | IT/Infra | Monthly | 10.0.1.98, 10.0.0.205, NAS | NOT EVIDENCED | NO | NO | Not evidenced | EXT-09 | NOT READY | NOT READY
CC7-08 | Security (CC7 System operations) | Incidents are handled | Incident response plan, severity, containment, CERT-In reporting, post-incident review | ISMS lead | Per incident; annual test | Organisation | NOT EVIDENCED; IF-01 not yet handled as an incident; docs/security/policies/05_Incident_Response_Plan.md and templates/incident_record.md (DRAFT); CKAM_URGENT_PRODUCTION_SECURITY_RUNBOOK.md phase 13 (prepared, not executed) | NO | NO | No plan | EXT-20, EXT-03 | NOT READY | NOT READY
CC7-09 | Security (CC7 System operations) | Malware is prevented | Antimalware/EDR on servers and NAS | IT/Infra | Continuous | Servers | NOT EVIDENCED | NO | NO | Not evidenced | EXT-37 | NOT READY | NOT READY
CC7-10 | Security (CC7 System operations) | Failures of the audit trail itself are visible | If an audit or log row cannot be written, the failure is reported on its first occurrence and then at most once a minute with a running count (error log kind log_write_failed plus a system_event row) | Dev lead; IT/Infra | Continuous | CKAM | backend/app/observability/writer.py; backend/tests/observability/test_log_write_failure_reporting.py (ca94574) | YES (code) / NO (production) | NO | Not deployed; no alert on the line (EXT-48); the Logs > Diagnostics screen does not show the count yet | EXT-01, EXT-48 | READY IN CODE - NOT DEPLOYED | NEW 2026-10-16
CC8-01 | Security (CC8 Change management) | Changes are authorised | Owner approves each push; separate owner approval for each production deploy | CKAM owner | Per change | CKAM | CLAUDE.md; git history; approval itself recorded only in chat sessions; docs/security/policies/04_Change_Management_Procedure.md and templates/change_record.md (DRAFT); 22 local security commits awaiting push approval | PARTIAL | NO | Approval not recorded as evidence | Change record (EXT-35) | PARTIAL | PARTIAL
CC8-02 | Security (CC8 Change management) | Changes are tested before release | Backend pytest on ckam_test; frontend tsc + vitest; E2E; security regression tests | Dev lead | Per change | CKAM | CLAUDE.md rule 4; backend/tests (about 1,783 tests; final run number from the lead); frontend 1,239 tests in 90 files; frontend/e2e incl. security.spec.ts (14/14 security journeys + 11 permanent journeys, 1 skipped); docs/security/CKAM_VAPT_REPORT.md; Final local run at HEAD fd34520: backend 2541 passed, 1 skipped; frontend tsc clean, vitest 1257 passed in 92 files, npm run build and check:build OK; Playwright 11 passed, 1 skipped; security journeys 14/14 (supersedes the 2026-10-15 figures) | PARTIAL | NO (no CI run history) | No CI; test results kept only in reports, not per change (IF-17) | CI (EXT-28); attach test output to change record | PARTIAL | PARTIAL
CC8-03 | Security (CC8 Change management) | Database changes are controlled | Schema change only by Alembic migration; never create_all at runtime | Dev lead | Per change | PostgreSQL | CLAUDE.md rule 3; backend/app/alembic/versions (41 committed migrations at HEAD d04779a, single head); alembic current at deploy; 43 committed migrations at HEAD fd34520, single head c6e8a0b2d4f6 (4 added by the security programme, not deployed) | YES | SOURCE EXISTS - alembic_version + git history | None | Keep | READY | READY
CC8-04 | Security (CC8 Change management) | Deployments are reproducible and reversible | Backup, exact release by commit, migration, restart, smoke checks, rollback folders | IT/Infra; Dev lead | Per deploy | 10.0.1.98 | docs/ai/PRODUCTION_INFRASTRUCTURE.md (deploy steps and 2026-10-14 notes); system_event app_started with version; ops/windows/ reference launcher, deploy, verify and rollback templates (secret-free; parser and -WhatIf validated); docs/security/CKAM_URGENT_PRODUCTION_SECURITY_RUNBOOK.md (prepared, NOT executed) | PARTIAL | PARTIAL (system_event app_started; launcher log) | Live launcher and release script not in git (EXT-13); reference templates not yet confirmed against the server; runbook never executed | EXT-13, EXT-35 | PARTIAL | PARTIAL
CC8-05 | Security (CC8 Change management) | Emergency changes are controlled | Emergency change procedure (e.g. IF-01) with after-the-fact approval and review | CKAM owner | Per emergency | CKAM | NOT EVIDENCED; docs/security/policies/04_Change_Management_Procedure.md emergency path (DRAFT); EXT-42 (IF-01 emergency change record) prepared | NO | NO | No procedure | EXT-35 | NOT READY | NOT READY
CC8-06 | Security (CC8 Change management) | Code is developed securely | Security baseline, guardrails, file-security review, authorization tests | Dev lead | Per change | CKAM | docs/security/CKAM_SECURITY_BASELINE.md; docs/ai/DEVELOPMENT_GUARDRAILS.md (security rules committed in da790d1); docs/security/CKAM_SECURITY_BASELINE.md updated 2026-10-16 with the closure rules | PARTIAL | NO | Baseline not yet approved; not evidenced per change | Approve baseline; checklist in change record | PARTIAL | PARTIAL
CC8-07 | Security (CC8 Change management) | Dependencies are controlled | Lock/constraints for Python; npm lock; audit before adding/upgrading | Dev lead | Per change | CKAM | frontend/package-lock.json; backend/constraints.txt (IF-11 FIXED in code); docs/security/evidence/closure/backend/dependency_recheck.md (python-jose / ecdsa no fixed version, not reachable, ACCEPTED; PyJWT replacement recommended, EXT-47) | PARTIAL | NO | Production install not yet using constraints.txt | EXT-12 | PARTIAL | PARTIAL
CC9-01 | Security (CC9 Risk mitigation) | Suppliers are managed | Supplier register and review (ERP team, NAS, GitHub, AI coding assistant provider, Google Fonts) | Management | Annual | Organisation | NOT EVIDENCED; docs/security/policies/09_Supplier_Security_Review.md (DRAFT) | NO | NO | No supplier review | EXT-34 | NOT READY | NOT READY
CC9-02 | Security (CC9 Risk mitigation) | Business disruption is planned for | BCP covering CKAM outage, data loss and ransomware | Management; IT/Infra | Annual | Organisation | NOT EVIDENCED; docs/security/policies/08_Business_Continuity_and_DR_Plan.md (DRAFT) | NO | NO | No BCP | EXT-29 | NOT READY | NOT READY
A1-01 | Availability | Capacity is sufficient | Monitor disk, DB size, slow requests and slow SQL | IT/Infra | Monthly | CKAM; servers | error_log slow_request / slow_sql rows; GET /api/admin/diagnostics/db | PARTIAL | SOURCE EXISTS - error_log kept 180 days | No thresholds or review | EXT-22 | PARTIAL | PARTIAL
A1-02 | Availability | Data is backed up daily | Nightly pg dump of ckassetmanagement, 30 days kept | IT/Infra | Daily | 10.0.0.205 | docs/ai/PRODUCTION_INFRASTRUCTURE.md (backup.log on DB server) | PARTIAL | SOURCE EXISTS - backup.log; no observation period | Same server, unencrypted; NAS files not evidenced (IF-08) | EXT-08 | PARTIAL | PARTIAL
A1-03 | Availability | Backups survive loss of the server | Encrypted off-server copy of DB dumps and NAS documents | IT/Infra | Daily | Backup target | NOT EVIDENCED; docs/security/CKAM_BACKUP_RESTORE_PLAN.md (prepared, not implemented) | NO | NO | No off-server copy | EXT-08 | NOT READY | NOT READY
A1-04 | Availability | Backups can be restored | Quarterly restore test into a throw-away database with row-count checks | IT/Infra | Quarterly | 10.0.0.205 | Dev drill only (docs/ai/AM-09_RC_FULL_AUDIT_REPORT.md; ops/test_backup_restore.sh, dev-only); docs/security/CKAM_BACKUP_RESTORE_PLAN.md and policies/templates/restore_test_record.md (prepared, never run) | NO | NO | Never restored in production | EXT-08 | NOT READY | NOT READY
A1-05 | Availability | Recovery objectives are defined | DR plan with RTO/RPO, reboot test, rollback incl. DB restore | Management; IT/Infra | Annual | CKAM | docs/ai/PRODUCTION_INFRASTRUCTURE.md (rollback needs DB restore; reboot test still open); docs/security/policies/08_Business_Continuity_and_DR_Plan.md (DRAFT) | NO | NO | No RTO/RPO; reboot test open | EXT-29 | NOT READY | NOT READY
A1-06 | Availability | The service restarts and reports health | Scheduled task restart; /api/health; diagnostics/health; startup/shutdown events | IT/Infra | Continuous | 10.0.1.98 | docs/ai/PRODUCTION_INFRASTRUCTURE.md; system_event startup/shutdown; GET /api/admin/diagnostics/health | PARTIAL | SOURCE EXISTS - system_event kept 180 days | No external uptime check | EXT-22 | PARTIAL | PARTIAL
C1-01 | Confidentiality | Confidential information is identified and restricted | Vendor commercial data, PO values, invoices, documents restricted by role, company and work area | ISMS lead; Dev lead | Annual classification; continuous enforcement | CKAM | docs/security/evidence/access/tests.csv; AC-1 fix (vendor contacts no longer readable by Own Assets Only, pending retest); AC-1 fix retested in closure retests 1 and 2 (not deployed) | PARTIAL | SOURCE EXISTS - DOCUMENT_DOWNLOADED and EXPORT rows | No classification scheme | Classification (A.5.12) | PARTIAL | PARTIAL
C1-02 | Confidentiality | Confidential information is retained and disposed of per policy | Log retention 180 days; audit kept forever; guarded audit purge; no business-data deletion | Management; Legal | Annual | CKAM | docs/ai/LOGGING_AND_DIAGNOSTICS.md section 4; system_event retention/purge_finished | PARTIAL | SOURCE EXISTS - purge_finished events | No approved retention schedule | EXT-21, EXT-31 | PARTIAL | PARTIAL
C1-03 | Confidentiality | Exports are controlled and traceable | Role-restricted exports; every export audited with filters and row count; formula injection neutralised | Dev lead | Continuous | CKAM | docs/ai/LOGGING_AND_DIAGNOSTICS.md (EXPORT rows); docs/security/evidence/input/formula_export_cell.txt | YES | SOURCE EXISTS - no observation period | None | Keep | READY | READY
C1-04 | Confidentiality | Secrets never reach code, logs or audit | No secrets in repo; redaction by key and value pattern; diagnostics bundle clean | Dev lead | Continuous | CKAM | Secrets scan (none in working tree or 282 commits); docs/security/evidence/auth/tests.csv AU-T049, AU-T089, AU-T090; backend/tests/observability/test_redaction.py; Closure secret scan (regex only): working tree, 299+ commits, built frontend, image layers and container env hold no real secret (docs/security/evidence/closure/retest2/infra/raw/secret_scan_summary.txt); refresh-token ids stored only as SHA-256 | YES | SOURCE EXISTS - test runs | None | Keep scan in release checklist | READY | READY
C1-05 | Confidentiality | Development copies of data are protected | Dev PC ACL, disk encryption, minimum real data in dev | Dev lead; IT | Quarterly | Dev PC 10.0.0.47 | IF-09; docs/ai/ERP_INTEGRATION.md (dev ERP copy of real data); docs/security/evidence/closure/infra/IF-09_ACL_PLAN.md (plan only; nothing changed on the dev PC) | NO | NO | Dev .env and dumps readable by too many accounts | EXT-10 | NOT READY | NOT READY
PI1-01 | Processing Integrity | Inputs are complete and valid | Schema validation (pydantic), 422 with every problem, size limits, quantity 1..1,000 | Dev lead | Continuous | CKAM API | docs/security/evidence/input/tests.csv; docs/security/evidence/auth/tests.csv AU-T069..AU-T078 | YES | N/A (configuration) | None | Keep | READY | READY
PI1-02 | Processing Integrity | A request is processed once | Idempotency keys per actor on write requests; replay and conflict audited | Dev lead | Continuous | CKAM API | backend/app/core/idempotency.py; docs/security/evidence/access/tests.csv (7 idempotency/business-logic cases); audit IDEMPOTENT_REPLAY / IDEMPOTENT_CONFLICT | YES | SOURCE EXISTS - ACCESS rows | None | Keep | READY | READY
PI1-03 | Processing Integrity | Asset history is complete and unalterable | apply_event / apply_events single writer of status, holder, status_since; asset_event append-only; asset_code immutable | Dev lead; DBA | Continuous | CKAM; PostgreSQL | backend/app/lifecycle/service.py; docs/security/evidence/infra/db_02_triggers_constraints.out.txt; db_03 A9 (status column has no DB-level guard); migration c6e8a0b2d4f6_asset_lifecycle_fields_guard.py; backend/tests/lifecycle/test_obs_status_guard.py (closure, not deployed) | YES | SOURCE EXISTS - asset_event | DB guard not deployed; anyone with SQL as the app role can set the marker (R-36); the strong barrier is the role split (EXT-07) | Role split (EXT-07) | READY | READY
PI1-04 | Processing Integrity | Bulk operations are all-or-nothing | Receive and Add Assets check everything first then write in one transaction | Dev lead | Continuous | CKAM | docs/ai/DECISIONS.md 2026-10-14 (6) | YES | SOURCE EXISTS - audit RECEIVE / BATCH_ADD rows | None | Keep | READY | READY
PI1-05 | Processing Integrity | Unique identity of assets | Unique asset code, case-insensitive unique serial (N/A exempt), unique PO per company | Dev lead | Continuous | PostgreSQL | docs/security/evidence/infra/db_02_triggers_constraints.out.txt; docs/security/evidence/infra/db_05_data_integrity.out.txt; backend/tests/masters/test_wpf2_category_names.py (one active category/sub-category name per work area); backend/tests/core/test_wpf2_serial_race_message.py (friendly 422 for the loser of a same-serial race) | YES | SOURCE EXISTS | db_05 shows 2 dev-stack observations to explain (two primary owners; user id 1 without a CREATE audit row) | Explain/clean dev observations | READY | READY
PI1-06 | Processing Integrity | ERP data is read, never written | ERP role read-only; every connection sets default_transaction_read_only; code issues SELECT only; create re-reads the copy | Dev lead; ERP owner | Continuous | ERP 10.0.1.69 | docs/ai/ERP_INTEGRATION.md; backend/app/erp/source.py; backend/tests/erp/test_vapt_erp_limits.py (IF-10 FIXED: timeouts, read-only); system_event erp_sync; backend/tests/erp/test_erp_tls_settings.py (PO_SOURCE_SSLMODE / PO_SOURCE_SSLROOTCERT, default prefer) | PARTIAL | SOURCE EXISTS - erp_sync_run, system_event | TLS settable but not mandatory; ERP owner must confirm TLS and the SELECT-only grant (EXT-25); timeouts not deployed | EXT-25 | PARTIAL | PARTIAL
PI1-08 | Processing Integrity | Concurrent requests do not create duplicates | Same-name creation is serialized (vendor, brand, category / sub-category per work area, also in Excel imports); parallel receive, idempotency, serial and move bursts create no duplicates and no over-receiving | Dev lead | Continuous | CKAM API | backend/tests/core/test_security_concurrency.py (RACE-1 FIXED, commit da790d1); backend/tests/masters/test_import_duplicate_names.py; backend/tests/masters/test_wpf2_category_names.py; docs/security/evidence/closure/retest2/sessions/concurrency_results.md (bursts x20: no duplicates, no 500, no deadlock) | YES (code) / NO (production) | N/A (configuration) | Not deployed | EXT-01 | READY IN CODE - NOT DEPLOYED | PARTIAL
PI1-07 | Processing Integrity | Exports are safe to open | Leading apostrophe on values starting with = + - @ in every export | Dev lead | Continuous | CKAM | docs/security/evidence/input/formula_export_cell.txt | YES | N/A (configuration) | None | Keep | READY | READY
P-01 | Privacy | People are told what personal data is kept | Privacy notice for staff and store users (names, codes, emails, phones, IP addresses in logs) | Legal; HR | Annual | CKAM | NOT EVIDENCED | NO | NO | No notice | EXT-31 | NOT IN SCOPE | NOT IN SCOPE
P-02 | Privacy | Personal data is limited and access-controlled | Only needed fields; logs head-office admin only; redaction | Dev lead | Continuous | CKAM | docs/ai/LOGGING_AND_DIAGNOSTICS.md section 9 | PARTIAL | SOURCE EXISTS - LOGS_VIEWED rows | No PII review | Review fields with legal (EXT-31) | PARTIAL | PARTIAL
P-03 | Privacy | Personal data requests and retention are handled | Process for access/correction requests and PII retention within append-only design | Legal | Per request | CKAM | NOT EVIDENCED | NO | NO | No process | EXT-31 | NOT IN SCOPE | NOT IN SCOPE
P-04 | Privacy | Personal data is not disclosed to third parties unnecessarily | Fonts loaded from Google send user IP addresses to a third party | Dev lead | Continuous | CKAM frontend | frontend/index.html; frontend/src/fonts.css (self-hosted Inter + IBM Plex Mono, 79dbae7); CSP without Google hosts (b401e9f); docs/security/evidence/closure/retest2/infra/raw/fonts_csp_playwright_summary.txt (0 Google requests) | YES (code) / NO (production) | N/A | Not deployed: production 3b5e842 still loads Google Fonts | EXT-01 (EXT-11 code side done) | READY IN CODE - NOT DEPLOYED | PARTIAL